## Sheet1
YILO KROBO MUNICIPAL ASSEMBLY 2020 COMPOSITE ANNUAL ACTION PLAN
ADOPTED GOAL:Creat Opportunities For All Ghanaians
PROGRAMME | SUB-PROGRAMME | ACTIVITY/PROJECT/OPERATION | LOCATION | BASELINE | OUTPUT INDICATOR | QUARTERLY TIME SCHEDULE |  |  |  | FUNDING SOURCE |  |  |  |  | IMPLEMENTING AGENCIES
[6 empty] | 1ST | 2ND | 3RD | 4TH | DACF | GoG | RFG | MP's FUND | IGF | LEAD | COLLABORATOR
EDUCATION
Social Service Delivery | Education & Youth Development | Construction of perimetre fence-wall at Somanya Presby school | Somanya |  | Fence-wall constructed | X | X | X | X | 90000 |  |  |  |  | GES | MWD
|  | Construction of 1No.2-unit classroom block,office,store and 2-seater KVIP | Sokwenya |  | Classroom constructed | X | X | X | X |  |  |  | 220000 |  | GES | MWD
|  | Repainting of Klo-Agogo SHS | Klo-Agogo |  | SHS repainted | X | X | X | X |  |  |  | 50000 |  | GES | MWD
|  | Construction of 1No.2-unit classroom block,office & store | Trawa |  | Classroom blk,office & store constructed | X | X | X | X |  |  |  | 234000 |  | GES | MWD
|  | Self-help projects/community initiated/conterpart funding | Selected community |  | Projected supported | X | X | X | X | 100000 |  |  |  |  | YKMA
|  | Supply of furniture for Somanya Methodist | Somanya |  | Furniture supplied | X | X | X | X |  |  | 50000 |  |  | GES | MWD
|  | Construction of 1No.3-unit classroom block,office,store & 1No.3-seater KVIP | Obawale |  | Classroom constructed | X | X | X | X |  |  | 300000 |  |  | GES | MWD
|  | Construction of 1No.2-storey classroom block with ancillary facility for Somanya Methodist school | Somanya |  | Classroom block constructed | X | X | X | X |  |  | 497000 |  |  | GES | MWD
|  | Construction of 1No.3-unit classroom block,office,store & 1No.3-seater KVIP | Tsrematin-Yoyim |  | Classroom block constructed | X | X | X | X | 234000 |  |  |  |  | GES | MWD
|  | Construction of 1No.3-unit classroom block,office,store & 1No.3-seater KVIP | Brukum-Agavenya |  | Classroom block constructed | X | X | X | X | 245000 |  |  |  |  | GES | MWD
|  | Cladding of 1No.6-unit classroom block for M/A primary | Sikalehia |  | Classroom block cladded | X | X | X | X | 243000 |  |  |  |  | GES | MWD
|  | Construction of 1No.semi-detached teachers' bungalow | Sra |  | Teachers bungalow constructed | X | X | X | X |  |  | 197000 |  |  | GES | MWD
|  | National day celebration(Independence day celebration | Somanya |  |  | X | [7 empty] | 20000 | GES | MWD
|  | District education fund-support brilliant but needy students and STME | Municipality-wide |  | Student supported | X | X | X | X | 45000 |  |  |  |  | GES | MWD
HEALTH
| Health Delivery | Complete construction of Akorley CHPs compound | Akorley |  | CHPs completed | X | X | X | X | 245000 |  |  |  |  | GHS | MWD
|  | Construction of 2No bedroom,semi-detached,borehoole & clinic facility | Klo-Agogo and Akorwu Bana |  | 2Nobedroom and clinic constructed | X | X | X | X | 76000 |  |  |  |  | GHS | MWD
|  | Construction of CHPs compound with mechanised borehole | Huhunya |  | CHPs compound constructed | X | X | X | X | 245000 |  |  |  |  | GHS | MWD
|  | Construction of CHPs compound with mechanised borehole | Aketebuor |  | CHPs compound constructed | X | X | X | X |  |  | 347000 |  |  | GHS | MWD
|  | Construction ofCHPs compound | Ahinkwa |  | CHPs compound constructed | X | X | X | X | 253000 |  |  |  |  | GHS | MWD
|  | Support the fight against COVID-19 | Municipality-wide |  | Fight against COVID-19 supported | X | X | X | X |  |  |  |  | 40000 | GHS | YKMA
|  | District Response Initiative-prevention of HIV/AIDS and malaria | Municipality-wide |  | Response supported | X | X | X | X | 20000 |  |  |  |  | GHS | YKMA
ADOPTED GOAL:Saveguard The Natural Environment & Ensure A Resilient, Built Environment
CLIMATE CHANGE AND ENVIRONMENT
Environmental & Sanitation management | Disaster Prevention & Management | Complete construction of storm drains at Somanya lorry park | Somanya |  | Storm drain constructed | X | X | X | X | 45000 |  |  |  |  | NADMO | MWD
|  | Construction of 10meter storm drain | Agavenya |  | Storm drain constructed | X | X | X | X | 50000 |  |  |  |  | NADMO | MWD
|  | Disaster preparedness and management | Municipality-wide |  | Disaster preparedness and management supported | X | X | X | X | 89000 |  |  |  |  | NADMO | YKMA
|  | Street Naming & property addressing exercise | Pilot areas |  |  | X | X | X | X | 50000 |  |  |  |  | PPD | YKMA
|  | Designing of layout for 2no. Communities | Pilot areas |  |  | X | X | X | X | 5000 |  |  |  |  | PPD | YKMA
|  | Picking of details and developing base map for 2no.communities | Pilot areas |  |  | X | X | X | X | 5000 |  |  |  |  | PPD | YKMA
|  | Embark on development control | Municipality-wide |  | Development control exercise embarked upon | X | X | X | X |  |  |  |  | 6000 | MWD | PPD/YKMA
|  | Procure 100No.street light | Somanya |  |  | X | X | X | X | 100000 |  |  |  |  | YKMA
|  | Procure accessories for the maintenance of street light | Somanya |  |  | X | X | X | X | 50000 |  |  |  |  | YKMA
|  | Purchase and documentation of lands for development projects | Somanya |  |  | X | X | X | X | 120000 |  |  |  |  | YKMA
|  | Fill up land sites with earth materials,plant trees to recalim the lands to its natural state | Municipality-wide |  |  | X | X | X | X |  |  | 12000 |  |  | NADMO | YKMA
|  | Educate and sensitize the public on bushfire,rain storm,road accident and flooding. | Municipality-wide |  |  | X | X | X | X | 5000 |  |  |  | 2000 | NADMO | YKMA
WATER & SANITATION
|  | Complete construction of 1No.10-seater W/C with mechanised borehole | Ogome |  | 10-seater KVIP and borehole constructed | X | X | X | X | 70000 |  |  |  |  | MEHU | YKMA
|  | Complete construction of 1No.10-seater W/C with mechanised borehole | Abokobi |  | 10-seater KVIP and borehole constructed | X | X | X | X | 63000 |  |  |  |  | MEHU | YKMA
|  | Construction of 15No.boreholes and 3No.iron removal plant | 15No selected communities |  | 15No.borehole and 3No.iron removal plant constructed | X | X | X | X |  |  | 250000 |  |  | MWD | YKMA
|  | Construction of 3No.borehole | Plechie,Brukum-Maumi & Abrewanko |  | 3No.borehole constructed | X | X | X | X |  |  |  | 34000 |  | MWD | YKMA
|  | Construction of slaughterhouse | Somanya |  | Slaughterhouse constructed | X | X | X | X |  |  | 374000 |  |  | BAC | YKMA
|  | Provision of water & filling of lowland | Nkurakan |  | Filling of lowland and provision of water undertaken | X | X | X | X |  |  | 73000 |  |  | MWD | YKMA
|  | Provision of water facilities at Roundabout,Akutunya & Klo-Agogo markets | Somanya(Roundabout),Somanya(Akutunya) & Klo-Agogo |  | Provision of water undertaken | X | X | X | X |  |  | 173000 |  |  | MWD | YKMA
|  | Disinfestation,disinfection and maintenance of solid and liquid waste disposal sites | Municipality-wide |  | Disinfestation and diinfection undertaken | X | X | X | X | 200000 |  |  |  |  | YKMA | MEHU
|  | Management of final waste disposal site | Municipality-wide |  | Final waste disposal site managed | X | X | X | X | 120000 |  |  |  |  | YKMA | MEHU
|  | Sanitation improvement package | Municipality-wide |  | Sanitation improved | X | X | X | X | 60000 |  |  |  |  | YKMA | MEHU
|  | Evacuate refuse from dumping sites to final disposal site | Municipality-wide |  | Refuse evacuated | X | X | X | X | 160000 |  |  |  |  | YKMA | MEHU
Infrastructure Delivery & Management | Infrastructure Development | URBAN ROADS / FEEDER ROADS/INFRASTRUCTURE
|  | Construction of access road to fertilizer factory | Trayonya junction |  | Access road constructed | X | X | X | X | 45000 |  |  |  |  | DUR | YKMA
|  | Reshaping of 8km selected feeder roads. | Municipality Wide |  | Feeder roads reshaped | X | X | X | X | 50000 |  |  |  |  | MWD | YKMA
|  | Preparation of Operation and maintenance plan | Municipality-wide |  | Operation and maintenance undertaken | X | X | X | X |  |  |  |  | 2000 | MWD | YKMA
|  | Embark on patching of potholes within somanya | Somanya |  |  | X | X | X | X
ADOPTED GOAL:Maintain A stable,United & Safe Society
SOCIAL PROTECTION
SECURITY
Management & Administration | Human Resource development & Management | Construction of police post | Klo-Agogo |  | Police post constructed | X | X | X | X | 147000 |  |  |  |  | YKMA | MWD
|  | Renovate of Somanya High court | Somanya |  | High court renovated | X | X | X | X | 70000 |  |  |  |  | YKMA | MWD
|  | Revision of Assembly by-laws | Somanya |  | By-laws revised | X | X | X | X | 30000 |  |  |  | 20000 | YKMA
|  | Renovate the magistrate,human resource,MPO and budget bungalows | Somanya |  | Bungalows renovated | X | X | X | X | 70000 |  |  |  |  | YKMA
|  | Erection of road safety sign posts within Somanya township. | Somanya |  |  | X | X | X | X | 7000
|  | Organise 2-day radio programme on road safety issues by Road Safety Commission | Somanya |  |  | X | X | X | X | 5600
|  | Renovation of office,accommodation,construction of 2No.cells and 3-seater W/C,for district magistrate court | Somanya |  | Renovation undertaken | X | X | X | X | 80000 |  |  |  |  | YKMA
VULNERABILITY
Disability
|  | Conduct physical,medical and psychological needs assessement for 5No. Vulnerable groups. | Somanya |  | PWD activities supported | X | X | X | X | 2000 |  |  |  |  | DSWCD | YKMA
|  | Identify, register and organise skills training for 200 persons with disability by the end of december 2020. | Somanya |  | Disables identified and trained | X | X | X | X | 2000 |  |  |  |  | DSWCD | YKMA
|  | Enrol and review NHIS cards for OVC, LEAP beneficiaries and PWDs. | Somanya |  | NHIS cards for OVC,LEAP benefiaries reviewed | X | X | X | X | 1000 |  |  |  |  | DSWCD | YKMA
Child Protection/Social Protection
|  | Facilitate the implementation of the livelihood empowerment against poverty activities bi-monthly for 1447 beneficiariey household | Somanya |  |  | X | X | X | X | 2000 |  |  |  |  | DSWCD | YKMA
|  | Identify,maintain and update data on various groups in the communities by the end of the year | Selected deprived communities |  |  | X | X | X | X | 1200 |  |  |  |  | DSWCD | YKMA
|  | Provide probation services to five juvinals by the end of December 2020 |  |  |  | X | X | X | X | 1200 |  |  |  |  | DSWCD | YKMA
|  | Provide hospital welfare services, assistant to destitute psychiatry patient and the standard ,20(twenty) clients and conduct needs assessment for 10 vulnerablr groups by the end of December 2020. | Municipality wide |  |  | X | X | X | X | 1500 |  |  |  |  | DSWCD | YKMA
|  | Intervene in cases of children in worst forms of child labour | Somanya |  |  | X | X | X | X | 1000 |  |  |  |  | DSWCD | YKMA
|  | Involve in weekly family tribunal sitting and provide probation services to 5(five) juviniles by the end of December 2020 | Somanya |  |  | X | X | X | X | 500 |  |  |  |  | DSWCD | YKMA
|  | General case work management, including support to the families and individuals in 50(fifty) non-child maintainance cases, custody, paternity, family reconciliation by the end of the year 2020 | Somanya |  |  | X | X | X | X | 1000 |  |  |  |  | DSWCD | YKMA
|  | Provide alternative care to 20(twenty) children without parental support, handle domestic violence cases, spousal abuse, trafficked children and street children by the end of the year 2020 | Somanya |  |  | X | X | X | X | 4000 |  |  |  |  | DSWCD | YKMA
|  | Supervise, monitor and facilitate the registration of 40(fourty) day care centres Quarterly. | Somanya |  |  | X | X | X | X | 1000 |  |  |  |  | DSWCD | YKMA
|  | To facilitate the roll out of the child protection tool kits through community engagement and dialogue to be done by the end of the year. | Somanya |  |  | X | X | X | X | 578 |  |  |  |  | DSWCD | YKMA
The Aged
[6 empty] | X | X | X | X
[6 empty] | X | X | X | X
[6 empty] | X | X | X | X
[6 empty] | X | X | X | X
Gender
|  | Revised and implement the municipal gender profile | Somanya |  |  | X | X | X | X | 5000 |  |  |  |  | YKMA
|  | Sensitisation programme on gender |  |  |  | X | X | X | X | 3000
|  | Education of reproductive health | [7 empty] | 3000
|  | Sensitisation programme on rape and where to get redress |  |  |  | X | X | X | X | 3000
PERFORMANCE AND REVENUE MOBILISTION
| Finance & Revenue Mobilisation | Preparation/Revision and Implementation of Revenue Improvement Action Plan | Somanya |  | Revenue improvement action plan and implemented | X | X | X | X | 50000 |  |  |  |  | FD | YKMA
|  | Set up task force to conduct quarterly revenue supervision & monitoring | Somanya |  | Task force formed | X | X | X | X |  |  |  |  | 2000 | FD | YKMA
|  | Encourage community-initiative projects through self-help to be done quarterly. | Somanya |  |  | X | X | X | X | 1200 |  |  |  |  | DSWCD | YKMA
|  | Conduct monthly meeting of the Finance & Administration sucommittee | Somanya |  | Finance and Administration meeting held | X | X | X | X | 20000 |  |  |  |  | FD | YKMA
|  | Conduct quarterly core management meeting to review revenue position of the Municipal assembly | Somanya |  | Quarterly management meeting held | X | X | X | X | 15000 |  |  |  |  | FD | YKMA
|  | Hold 10(ten) community briefing sessions on the role of the Assembly and its departments with key stakeholders and community members at the area councils by the end of the year | Somanya |  |  | X | X | X | X | 3000 |  |  |  |  | DSWCD | YKMA
|  | Mobilise and train voluntary leaders and community-based organisation as change agents in the community by the end of the second Quarter | Somanya |  |  | X | X | X | X | 1200 |  |  |  |  | DSWCD | YKMA
|  | Conduct quarterly meetings with revenue staff to review revenue performance of the Assembly | Somanya |  | Quarterly meeting with revenue collectors held | X | X | X | X | 5000 |  |  |  |  | FD | YKMA
|  | Valuation of immovable properties | Municipality Wide |  | Immovable properties evaluated | X | X | X | X | 60000 |  |  |  |  | YKMA | FD
|  | Train revenue staff and zonal council members on revenue collection | Somanya |  |  | X | X | X | X | 7000 |  |  |  |  | FD | YKMA
|  | Educate the public on the need to pay property rate and to acquire permanent and temporal permits | Municipality-wide |  |  | X | X | X | X |  |  |  |  | 5000 | YKMA | FD
| Human Resource Management | Renovation of Deputy Director's residence | Somanya |  | Residence renovated | X | X | X | X |  |  |  |  | 78000 | YKMA
|  | Goods and service for human resources and statistical offices | Somanya |  |  | X | X | X | X |  |  |  |  | 20000 | YKMA
|  | Renovate Assembly office building | Somanya |  |  | X | X | X | X | 500000 |  |  |  |  | YKMA
|  | Procurement 2no. Air conditioners |  |  |  | X | X | X | X | 5000 |  |  |  | 5000 | YKMA
|  | Procure 12No.swivel chairs,1No.office desk,2No.desk tops,2No.laptops,2No.printers & 2No.air conditioners | Somanya |  |  | X | X | X | X | 20000 |  |  |  | 20000 | YKMA
|  | Capacity building for staff & honourable members | Somanya |  | Staff and assembly members trained | X | X | X | X |  |  | 40000 |  |  | HRD | YKMA
|  | Renovate works department office | Somanya |  |  | X | X | X | X | 120000 |  |  |  |  | MWD | YKMA
|  | Procurement of furniture & fittings,office facilities,printed materials & stationary | Somanya |  | Funiture and fittings procured | X | X | X | X | 29000 |  |  |  |  | YKMA
|  | Procurement of 7no.desktops computers,7no.laptops,5no.printers,2no scanners & 7no. UPS | Somanya |  | Computer,printers and scanners procured | X | X | X | X | 50000 |  |  |  |  | YKMA
|  | Procurement 2no. Air conditioners | Somanya |  | Air condition procured | X | X | X | X | 10000 |  |  |  |  | YKMA
|  | Organise 3no.mandatory general assembly & 1no.special meetings | Somanya |  | Meetings held | X | X | X | X | 56000 |  |  |  |  | YKMA
|  | Organise 6no subcommittees and Execo committee meetings | Somanya |  | Meetings held | X | X | X | X | 60000 |  |  |  |  | YKMA
|  | Establishment & strengthening of sub-structures |  |  | Substructures established and strengthened | X | X | X | X | 100000 |  |  |  |  | YKMA
|  | Support the activities of traditional authorities | Somanya |  |  | X | X | X | X | 10000 |  |  |  | 10000 | YKMA
|  | Preparation & implementation of 2021 composite action plan,2021 budget & 2021 procurement plans, fee fixing resolution and DMTDP | Somanya |  | Document prepared | X | X | X | X | 160000 |  |  |  |  | YKMA
| Research,Statistics & Information management | Organisation of Stakeholder consultative/town hall meeting & public education | Zonal council level |  | Stakeholder meeting held | X | X | X | X | 20000 |  |  |  |  | YKMA
|  | Monitoring & Evaluation of projects & programmes | Municipality Wide |  | Monitoring and evaluation undertaken | X | X | X | X | 60000 |  |  |  |  | YKMA
|  | Hold 10(ten) community briefing sessions on the role of the Assembly and its departments with ket stakeholders and community members at the area councils by the end of the year | Somanya |  |  | X | X | X | X | 750 |  |  |  |  | DSWCD | YKMA
|  | Mobilise and train voluntary leaders and community-based organisation as change agents in the community by the end of the second Quarter | Somanya |  |  | X | X | X | X | 500 |  |  |  |  | DSWCD | YKMA
ADOPTED GOAL:Build A Prosperous Society
LOCAL ECONOMIC DEVELOPMENT
Economic Development | Trade,Tourism & Industrial Development | Construction of 1No. warehouse(23meters by 6meters) | Akutunya Market,Somanya |  | Warehouse constructed | X | X | X | X |  |  | 347000 |  |  | BAC | YKMA
|  | Construction of 5No.20-unit market-shed | Akutunya market,somanya |  | Market-shed constructed | X | X | X | X |  |  | 300000 |  |  | BAC | YKMA
|  | Construction of Kenkey shed | Somanya,Roundabout |  | Kenkey shed constructed | X | X | X | X |  |  |  | 78000 |  | BAC | YKMA
|  | Construction of 1No.10-unit market shed | Oterkpolu |  | Market-shed constructed | X | X | X | X |  |  |  | 280000 |  | BAC | YKMA
|  | Rehabilitation of Klo-Agogo market centre(Phase I) | Klo-Agogo |  | Market rehabilitated | X | X | X | X |  |  |  | 87000 |  | BAC | YKMA
|  | Construction of 1No.slaughterhouse | Somanya. |  | Training organised | X | X | X | X |  |  | 378000 |  |  | BAC | YKMA
|  | Support for government flagship programmes(1D1F) | Somanya |  |  | X | X | X | X | 10000 |  |  |  |  | BAC | YKMA
|  | Meeting with business community to identify their challenges. | Somanya |  |  | X | X | X | X |  |  |  |  | 3000 | BAC | YKMA
|  | Partner external bodies to offer employable and sustainable skills training for the youth | Somanya |  |  | X | X | X | X |  |  |  |  | 5000 | DSWCD | YKMA
|  | Promote and provide 6 alternative livelihood empowerment skills programmes for the deprived in the communities by the end of the year | Somanya |  |  | X | X | X | X |  |  |  |  | 4000 | DSWCD | YKMA
|  | Undertake quarterly joint monitoring and evaluation with MPCU | Municipality-wide |  |  | X | X | X | X | 6000 |  |  |  |  | BAC | YKMA
|  | Develop one tourist site | Huhunya |  |  | X | X | X | X | 900000 |  |  |  |  | BAC | YKMA
AGRICULTURE
|  | Introduce hybrid seed maize varieties to farmers | Municipality-wide |  |  | X | X | X | X |  | 20000 |  |  |  | MOFA | YKMA
|  | Conduct field demonstartions | Municipality-wide |  |  | X | X | X | X |  | 14000 |  |  |  | MOFA | YKMA
|  | Train farmers of hybrid maize,good agriculture Practices | Municipality-wide |  |  | X | X | X | X |  | 12000 |  |  |  | MOFA | YKMA
|  | facilitate control of fall Army Worm | Municipality-wide |  |  | X | X | X | X |  | 30000 |  |  |  | MOFA | YKMA
|  | Procure PPR and rabies vaccines | Municipality-wide |  |  | X | X | X | X |  | 40000 |  |  |  | MOFA | YKMA
|  | Creat awareness through community information systems | Municipality-wide |  |  | X | X | X | X |  |  |  |  | 2000 | MOFA | YKMA
|  | Mobilise and set up community vaccination centres | Municipality-wide |  |  | X | X | X | X |  | 3000 |  |  |  | MOFA | YKMA
|  | Organise 5 women groups | Municipality-wide |  |  | X | X | X | X |  | 2000 |  |  |  | MOFA | YKMA
|  | Training of selected women groups | Municipality |  |  | X | X | X | X |  | 4000 |  |  |  | MOFA | YKMA
|  | Linking women groups to credit sources | Municipality-wide |  | ` | X | X | X | X |  | 2000 |  |  |  | MOFA | YKMA
|  | Conduct scheduled disease survaillance for PPR,rabbies,new castle,CBPP & vaccinations | Somanya |  |  | X | X | X | X | 5000 |  |  |  |  | MOFA | YKMA
|  | Organise research and extension linkage committee meeting with 100 stakeholders | Somanya |  |  | X | X | X | X | 25000 |  |  |  |  | MOFA | YKMA
|  | Establishment of 4(1/2) acreas maize,4(1/2) acrea cassava,4(1/2) acrea pepper demonstration farms | Municipality Wide |  |  | X | X | X | X | 20000 |  |  |  |  | MOFA | YKMA
|  | Undertake data collection on major crops | Municipality Wide |  |  | X | X | X | X | 14000 |  |  |  |  | MOFA | YKMA
|  | Procurement of stationery and office consumables for department of agric | Somanya |  |  | X | X | X | X | 20000 |  |  |  |  | MOFA | YKMA
|  | Organise National Farmers Day | Somanya |  |  | X | X | X | X | 30000 |  |  |  |  | MOFA | YKMA
|  | Extension services,MAG & DCAT activities | Municipality-wide |  |  | X | X | X | X |  | 15000 |  |  |  | MOFA | YKMA

## Sheet2
PROJECTS/PROGRAMMES FOR 2020 BUDGET AND CORRESPONDING COST
| ACTIVITY/PROJECT/OPERATION | LOCATION | FUNDING SOURCE
|  |  | DACF | GoG | RFG | MP's FUND | IGF
1 | Construction of perimetre fence-wall at Somanya Presby school | Somanya | 90000 |  |  |  |  | 90000
2 | Construction of 1No.2-unit classroom block,office,store and 2-seater KVIP | Sokwenya |  |  |  | 220000 |  | 220000
3 | Repainting of Klo-Agogo SHS | Klo-Agogo |  |  |  | 50000 |  | 50000
4 | Construction of 1No.2-unit classroom block,office & store | Trawa |  |  |  | 234000 |  | 234000
5 | Self-help projects/community initiated/conterpart funding | Selected community | 100000 |  |  |  |  | 100000
6 | Supply of furniture for Somanya Methodist | Somanya |  |  | 50000 |  |  | 50000
7 | Construction of 1No.3-unit classroom block,office,store & 1No.3-seater KVIP | Obawale |  |  | 300000 |  |  | 300000
8 | Construction of 1No.2-storey classroom block with ancillary facility for Somanya Methodist school | Somanya |  |  | 397000 |  |  | 397000
9 | Construction of 1No.3-unit classroom block,office,store & 1No.3-seater KVIP | Tsrematin-Yoyim | 234000 |  |  |  |  | 234000
10 | Construction of 1No.3-unit classroom block,office,store & 1No.3-seater KVIP | Brukum-Agavenya | 245000 |  |  |  |  | 245000
11 | Cladding of 1No.6-unit classroom block for M/A primary | Sikalehia | 243000 |  |  |  |  | 243000
12 | Construction of 1No.semi-detached teachers' bungalow | Sra |  |  | 197000 |  |  | 197000
13 | National day celebration(Independence day celebration | Somanya |  |  |  |  | 20000 | 20000
14 | District education fund-support brilliant but needy students and STME | Municipality-wide | 45000 |  |  |  |  | 45000
15 | Complete construction of Akorley CHPs compound | Akorley | 245000 |  |  |  |  | 245000
16 | Construction of 2No bedroom,semi-detached,borehoole & clinic facility | Klo-Agogo and Akorwu Bana | 76000 |  |  |  |  | 76000
17 | Construction of CHPs compound with mechanised borehole | Huhunya | 245000 |  |  |  |  | 245000
18 | Construction of CHPs compound with mechanised borehole | Aketebuor |  |  | 347000 |  |  | 347000
19 | Construction ofCHPs compound | Ahinkwa | 253000 |  |  |  |  | 253000
20 | Support the fight against COVID-19 | Municipality-wide |  |  |  |  | 40000 | 40000
21 | District Response Initiative-prevention of HIV/AIDS and malaria | Municipality-wide | 20000 |  |  |  |  | 20000
22 | Complete construction of storm drains at Somanya lorry park | Somanya | 45000 |  |  |  |  | 45000
23 | Construction of 10meter storm drain | Agavenya | 50000 |  |  |  |  | 50000
24 | Disaster preparedness and management | Municipality-wide | 89000 |  |  |  |  | 89000
25 | Street Naming & property addressing exercise | Pilot areas | 50000 |  |  |  |  | 50000
26 | Designing of layout for 2no. Communities | Pilot areas | 5000 |  |  |  |  | 5000
27 | Picking of details and developing base map for 2no.communities | Pilot areas | 5000 |  |  |  |  | 5000
28 | Embark on development control | Municipality-wide |  |  |  |  | 6000 | 6000
29 | Procure 100No.street light | Somanya | 100000 |  |  |  |  | 100000
30 | Procure accessories for the maintenance of street light | Somanya | 50000 |  |  |  |  | 50000
31 | Purchase and documentation of lands for development projects | Somanya | 120000 |  |  |  |  | 120000
32 | Fill up land sites with earth materials,plant trees to recalim the lands to its natural state | Municipality-wide |  |  | 12000 |  |  | 12000
33 | Educate and sensitize the public on bushfire,rain storm,road accident and flooding. | Municipality-wide | 5000 |  |  |  | 2000 | 7000
34 | Complete construction of 1No.10-seater W/C with mechanised borehole | Ogome | 70000 |  |  |  |  | 70000
35 | Complete construction of 1No.10-seater W/C with mechanised borehole | Abokobi | 63000 |  |  |  |  | 63000
36 | Construction of 15No.boreholes and 3No.iron removal plant | 15No selected communities |  |  | 250000 |  |  | 250000
37 | Construction of 3No.borehole | Plechie,Brukum-Maumi & Abrewanko |  |  |  | 34000 |  | 34000
38 | Construction of slaughterhouse | Somanya |  |  | 374000 |  |  | 374000
39 | Provision of water & filling of lowland | Nkurakan |  |  | 73000 |  |  | 73000
40 | Provision of water facilities at Roundabout,Akutunya & Klo-Agogo markets | Somanya(Roundabout),Somanya(Akutunya) & Klo-Agogo |  |  | 173000 |  |  | 173000
41 | Disinfestation,disinfection and maintenance of solid and liquid waste disposal sites | Municipality-wide | 200000 |  |  |  |  | 200000
42 | Management of final waste disposal site | Municipality-wide | 120000 |  |  |  |  | 120000
43 | Sanitation improvement package | Municipality-wide | 60000 |  |  |  |  | 60000
44 | Evacuate refuse from dumping sites to final disposal site | Municipality-wide | 160000 |  |  |  |  | 160000
45 | Construction of access road to fertilizer factory | Trayonya junction | 45000 |  |  |  |  | 45000
46 | Reshaping of 8km selected feeder roads. | Municipality Wide | 50000 |  |  |  |  | 50000
47 | Preparation of Operation and maintenance plan (Rehabilitation of Assembly Properties | Municipality-wide |  |  |  |  | 348346.24 | 348346.24
48 | Embark on patching of potholes within somanya | Somanya | 50000 |  |  |  |  | 50000
49 | Construction of police post | Klo-Agogo | 147000 |  |  |  |  | 147000
50 | Renovate of Somanya High court | Somanya | 70000 |  |  |  |  | 70000
51 | Revision of Assembly by-laws | Somanya | 30000 |  |  |  | 20000 | 50000
52 | Renovate the magistrate,human resource,MPO and budget bungalows | Somanya | 70000 |  |  |  |  | 70000
53 | Erection of road safety sign posts within Somanya township. | Somanya | 7000 |  |  |  |  | 7000
54 | Organise 2-day radio programme on road safety issues by Road Safety Commission | Somanya | 5600 |  |  |  |  | 5600
55 | Renovation of office,accommodation,construction of 2No.cells and 3-seater W/C,for district magistrate court | Somanya | 80000 |  |  |  |  | 80000
56 | Conduct physical,medical and psychological needs assessement for 5No. Vulnerable groups. | Somanya | 2000 |  |  |  |  | 2000
57 | Identify, register and organise skills training for 200 persons with disability by the end of december 2020. | Somanya | 2000 |  |  |  |  | 2000
58 | Enrol and review NHIS cards for OVC, LEAP beneficiaries and PWDs. | Somanya | 1000 |  |  |  |  | 1000
59 | Facilitate the implementation of the livelihood empowerment against poverty activities bi-monthly for 1447 beneficiariey household | Somanya | 2000 |  |  |  |  | 2000
60 | Identify,maintain and update data on various groups in the communities by the end of the year | Selected deprived communities | 1200 |  |  |  |  | 1200
61 | Provide probation services to five juvinals by the end of December 2020 |  | 1200 |  |  |  |  | 1200
62 | Provide hospital welfare services, assistant to destitute psychiatry patient and the standard ,20(twenty) clients and conduct needs assessment for 10 vulnerablr groups by the end of December 2020. | Municipality wide | 1500 |  |  |  |  | 1500
63 | Intervene in cases of children in worst forms of child labour | Somanya | 1000 |  |  |  |  | 1000
64 | Involve in weekly family tribunal sitting and provide probation services to 5(five) juviniles by the end of December 2020 | Somanya | 500 |  |  |  |  | 500
65 | General case work management, including support to the families and individuals in 50(fifty) non-child maintainance cases, custody, paternity, family reconciliation by the end of the year 2020 | Somanya | 1000 |  |  |  |  | 1000
66 | Provide alternative care to 20(twenty) children without parental support, handle domestic violence cases, spousal abuse, trafficked children and street children by the end of the year 2020 | Somanya | 4000 |  |  |  |  | 4000
67 | Supervise, monitor and facilitate the registration of 40(fourty) day care centres Quarterly. | Somanya | 1000 |  |  |  |  | 1000
68 | To facilitate the roll out of the child protection tool kits through community engagement and dialogue to be done by the end of the year. | Somanya | 578 |  |  |  |  | 578
69 | Revised and implement the municipal gender profile | Somanya | 5000 |  |  |  |  | 5000
70 | Sensitisation programme on gender |  | 3000 |  |  |  |  | 3000
71 | Education of reproductive health |  | 3000 |  |  |  |  | 3000
72 | Sensitisation programme on rape and where to get redress |  | 3000 |  |  |  |  | 3000
73 | Preparation/Revision and Implementation of Revenue Improvement Action Plan | Somanya | 50000 |  |  |  |  | 50000
74 | Set up task force to conduct quarterly revenue supervision & monitoring | Somanya |  |  |  |  | 2000 | 2000
75 | Encourage community-initiative projects through self-help to be done quarterly. | Somanya | 1200 |  |  |  |  | 1200
76 | Conduct monthly meeting of the Finance & Administration sucommittee | Somanya | 20000 |  |  |  |  | 20000
77 | Conduct quarterly core management meeting to review revenue position of the Municipal assembly | Somanya | 15000 |  |  |  |  | 15000
78 | Hold 10(ten) community briefing sessions on the role of the Assembly and its departments with key stakeholders and community members at the area councils by the end of the year | Somanya | 3000 |  |  |  |  | 3000
79 | Mobilise and train voluntary leaders and community-based organisation as change agents in the community by the end of the second Quarter | Somanya | 1200 |  |  |  |  | 1200
80 | Conduct quarterly meetings with revenue staff to review revenue performance of the Assembly | Somanya | 5000 |  |  |  |  | 5000
81 | Valuation of immovable properties | Municipality Wide | 60000 |  |  |  |  | 60000
82 | Train revenue staff and zonal council members on revenue collection | Somanya | 7000 |  |  |  |  | 7000
83 | Educate the public on the need to pay property rate and to acquire permanent and temporal permits | Municipality-wide |  |  |  |  | 5000 | 5000
84 | Renovation of Deputy Director's residence | Somanya |  |  |  |  | 78000 | 78000
85 | Goods and service for human resources and statistical offices | Somanya |  |  |  |  | 20000 | 20000
86 | Renovate Assembly office building | Somanya | 200000 |  |  |  |  | 200000
87 | Procurement 2no. Air conditioners |  | 5000 |  |  |  | 5000 | 10000
88 | Procure 12No.swivel chairs,1No.office desk,2No.desk tops,2No.laptops,2No.printers & 2No.air conditioners | Somanya | 20000 |  |  |  | 20000 | 40000
89 | Capacity building for staff & honourable members | Somanya |  |  | 40000 |  |  | 40000
90 | Renovate works department office | Somanya | 120000 |  |  |  |  | 120000
91 | Procurement of furniture & fittings,office facilities,printed materials & stationary | Somanya | 29000 |  |  |  |  | 29000
92 | Procurement of 7no.desktops computers,7no.laptops,5no.printers,2no scanners & 7no. UPS | Somanya | 50000 |  |  |  |  | 50000
93 | Procurement 2no. Air conditioners | Somanya | 10000 |  |  |  |  | 10000
94 | Organise 3no.mandatory general assembly & 1no.special meetings | Somanya | 56000 |  |  |  |  | 56000
95 | Organise 6no subcommittees and Execo committee meetings | Somanya | 60000 |  |  |  |  | 60000
96 | Establishment & strengthening of sub-structures |  | 100000 |  |  |  |  | 100000
97 | Support the activities of traditional authorities | Somanya | 10000 |  |  |  | 10000 | 20000
98 | Preparation & implementation of 2021 composite action plan,2021 budget & 2021 procurement plans, fee fixing resolution and DMTDP | Somanya | 160000 |  |  |  |  | 160000
99 | Organisation of Stakeholder consultative/town hall meeting & public education | Zonal council level | 20000 |  |  |  |  | 20000
100 | Monitoring & Evaluation of projects & programmes | Municipality Wide | 60000 |  |  |  |  | 60000
101 | Hold 10(ten) community briefing sessions on the role of the Assembly and its departments with ket stakeholders and community members at the area councils by the end of the year | Somanya | 750 |  |  |  |  | 750
102 | Mobilise and train voluntary leaders and community-based organisation as change agents in the community by the end of the second Quarter | Somanya | 500 |  |  |  |  | 500
105 | Construction of 1No. warehouse(23meters by 6meters) | Akutunya Market,Somanya |  |  | 347000 |  |  | 347000
106 | Construction of 5No.20-unit market-shed | Akutunya market,somanya |  |  | 300000 |  |  | 300000
107 | Construction of Kenkey shed | Somanya,Roundabout |  |  |  | 78000 |  | 78000
108 | Construction of 1No.10-unit market shed | Oterkpolu |  |  |  | 280000 |  | 280000
109 | Rehabilitation of Klo-Agogo market centre(Phase I) | Klo-Agogo |  |  |  | 87000 |  | 87000
110 | Construction of 1No.slaughterhouse | Somanya. |  |  | 378000 |  |  | 378000
111 | Support for government flagship programmes(1D1F) | Somanya | 10000 |  |  |  |  | 10000
112 | Meeting with business community to identify their challenges. | Somanya |  |  |  |  | 3000 | 3000
113 | Partner external bodies to offer employable and sustainable skills training for the youth | Somanya |  |  |  |  | 5000 | 5000
114 | Promote and provide 6 alternative livelihood empowerment skills programmes for the deprived in the communities by the end of the year | Somanya |  |  |  |  | 4000 | 4000
115 | Undertake quarterly joint monitoring and evaluation with MPCU | Municipality-wide | 6000 |  |  |  |  | 6000
116 | Develop one tourist site | Huhunya | 900000 |  |  |  |  | 900000
117 | Introduce hybrid seed maize varieties to farmers | Municipality-wide |  | 20000 |  |  |  | 20000
118 | Conduct field demonstartions | Municipality-wide |  | 14000 |  |  |  | 14000
119 | Train farmers of hybrid maize,good agriculture Practices | Municipality-wide |  | 12000 |  |  |  | 12000
120 | facilitate control of fall Army Worm | Municipality-wide |  | 30000 |  |  |  | 30000
121 | Procure PPR and rabies vaccines | Municipality-wide |  | 40000 |  |  |  | 40000
122 | Creat awareness through community information systems | Municipality-wide |  |  |  |  | 2000 | 2000
123 | Mobilise and set up community vaccination centres | Municipality-wide |  | 3000 |  |  |  | 3000
124 | Organise 5 women groups | Municipality-wide |  | 2000 |  |  |  | 2000
125 | Training of selected women groups | Municipality |  | 4000 |  |  |  | 4000
126 | Linking women groups to credit sources | Municipality-wide |  | 2000 |  |  |  | 2000
127 | Conduct scheduled disease survaillance for PPR,rabbies,new castle,CBPP & vaccinations | Somanya | 5000 |  |  |  |  | 5000
128 | Organise research and extension linkage committee meeting with 100 stakeholders | Somanya | 25000 |  |  |  |  | 25000
129 | Establishment of 4(1/2) acreas maize,4(1/2) acrea cassava,4(1/2) acrea pepper demonstration farms | Municipality Wide | 20000 |  |  |  |  | 20000
130 | Undertake data collection on major crops | Municipality Wide | 14000 |  |  |  |  | 14000
131 | Procurement of stationery and office consumables for department of agric | Somanya | 20000 |  |  |  |  | 20000
132 | Organise National Farmers Day | Somanya | 30000 |  |  |  |  | 30000
133 | Extension services,MAG & DCAT activities | Municipality-wide |  | 15000 |  |  |  | 15000

## Sheet3
2020 REVENUE PROJECTIONS - IGF ONLY
ITEM | 2019 |  | 2020 Projection GH₵ | 2021 Projection GH₵ | 2022 Projection GH₵ | 2023 Projection GH₵
| Budget GH₵ | Actual as at July GH₵
Basic Rate | 2200 | 0 | 2200 | 2420 | 2662 | 2928.2
Property Rate | 220110.04 | 46775.24 | 220110.04 | 242121.044 | 266333.1484 | 292966.4632
Fees | 396166.2 | 162848.12 | 415974.51 | 457571.961 | 503329.1571 | 553662.0728
Fines | 25502 | 9126 | 141500 | 155650 | 171215 | 188336.5
Licenses | 473724.38 | 226052.41 | 478461.6238 | 526307.7862 | 578938.5648 | 636832.4213
Land | 174389.08 | 84711.65 | 163715.5 | 180087.05 | 198095.755 | 217905.3305
Rent | 146628.4 | 31404 | 148094.684 | 162904.1524 | 179194.5676 | 197114.0244
Investment | 164733.38 | 4640 | 113817.3 | 125199.03 | 137718.933 | 151490.8263
Miscellaneous | 4950 | 30000 | 4950 | 5445 | 5989.5 | 6588.45
Total | 1608403.48 | 595557.42 | 1688823.6578 | 1857706.0236 | 2043476.6259 | 2247824.2885

## Sheet4
2020 REVENUE PROJECTIONS - ALL REVENUE SOURCES
ITEM | 2019 |  | 2020 PROJECTION (GH₵) | 2021 PROJECTION (GH₵) | 2022 PROJECTION (GH₵) | 2023 PROJECTION (GH₵)
| Budget (GH₵) | Actual as at July (GH₵)
IGF | 1608403.47 | 595557.42 | 1688823.66 | 1857706.026 | 2043476.6286 | 2247824.2915
Compensation Transfer | 2480674.1 | 1756613.82 | 2338427 | 2572269.7 | 2829496.67 | 3112446.337
Goods and Services Transfer | 84097.74 | 0 | 91594.06 | 100753.466 | 110828.8126 | 121911.6939
DACF | 3418153.75 | 1323648.69 | 3800780.92 | 4180859.012 | 4598944.9132 | 5058839.4045
School Feeding | - | 0 | 0 | 0 | 0 | 0
DDF | 1062618.89 | 569308.44 | 612247.6 | 673472.36 | 740819.596 | 814901.5556
MP's Common Fund | 400000 | 213970.88 | 600000 | 660000 | 726000 | 798600
Other Transfers (CIDA/MOFA) | 191853.86 | 134297 | 191853.81 | 211039.191 | 232143.1101 | 255357.4211
Total | 9245801.81 | 4593396.25 | 9323727.05 | 10256099.755 | 11281709.7305 | 12409880.7036

## Sheet5
2020 EXPENDITURE PROJECTIONS - ALL FUNDING SOURCES
Expenditure Items | 2019 Budget GH₵ | Actual as at July, 2019 GH₵ | 2020 GH₵ | 2021 GH₵ | 2022 GH₵ | 2023 GH₵
Compensation | 2833859.45 | 2489996.22 | 2727746 | 3000520.6 | 3300572.66 | 3630629.926
Goods and Services | 2716375.504 | 943126.2 | 3295493.04 | 3625042.344 | 3987546.5784 | 4386301.2362
Assets | 3701566.86 | 1136217.83 | 3300488 | 3630536.8 | 3993590.48 | 4392949.528
Total | 9251801.814 | 4569340.25 | 9323727.04 | 10256099.744 | 11281709.7184 | 12409880.6902
2020 EXPENDITURE PROJECTIONS - IGF
Expenditure Items | 2019 Budget GH₵ | Actual as at July, 2019 GH₵ | 2020 GH₵ | 2021 GH₵ | 2022 GH₵ | 2023 GH₵
Compensation | 353185.35 | 180124.5285 | 389319 | 428250.9 | 471075.99 | 518183.589
Goods and Services | 853736.634 | 415402.89 | 961739.928 | 1057913.9208 | 1163705.3129 | 1280075.8442
Assets | 401481.49 | 0 | 337764.732 | 371541.2052 | 408695.3257 | 449564.8583
Total | 1608403.474 | 595527.4185 | 1688823.66 | 1857706.026 | 2043476.6286 | 2247824.2915

## Sheet6
SUMMARY OF EXPENDITURE BYDGET BY DEPARTMENT, ITEM AND FUNDING SOURCE – 2020
Department | Compensation | Goods & Services | Assets | Total | Source of Funding |  |  |  |  | Total
[5 empty] | Assembly’s IGF | GOG | DACF | DDF | OTHERS
Central Administration | 1571147 | 1197278.04 | 0 | 2768425.04 | 1275058.66 | 1181828.86 | 204999.92 | 106537.6 | 0 | 2768425.04
Works department | 183113 | 428729 | 1344716.14 | 1956558.14 | 372765 | 183113 | 1120680.14 | 280000 | 0 | 1956558.14
Department of Agriculture | 642617 | 266974 | 0 | 909591 | 2000 | 680737.19 | 35000 | 0 | 191853.81 | 909591
Social Development | 272674 | 206417 | 0 | 479091 | 2000 | 287052 | 190039 | 0 | 0 | 479091
Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Waste management |  | 739000 | 371299.86 | 1110299.86 | 15000 |  | 1095299.86 |  |  | 1110299.86
Urban Roads | 0 | 27228 | 389172 | 416400 | 0 | 27228 | 239172 | 150000 | 0 | 416400
Budget and rating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transport | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule 2 |  |  |  | 0 | [5 empty] | 0
Physical Planning | 58195 | 72867 | 30000 | 161062 | 21000 | 70062 | 70000 | 0 | 0 | 161062
Trade and Industry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Education youth and sports | 0 | 330000 | 928162 | 1258162 | 1000 | 0 | 581452 | 75710 | 600000 | 1258162
Disaster Prevention and Management | 0 | 8000 | 0 | 8000 | 0 | 0 | 8000 | 0 | 0 | 8000
Natural res conservation | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Health | 0 | 19000 | 237138 | 256138 | 0 | 0 | 256138 | 0 | 0 | 256138
TOTALS | 2727746 | 3295493.04 | 3300488 | 9323727.04 | 1688823.66 | 2430021.05 | 3800780.92 | 612247.6 | 791853.81 | 9323727.04