## Sheet1
2021 COMPOSITE ANNUAL ACTION PLAN
ADOPTED GOAL:Creat Opportunities For All Ghanaians
PROGRAMME | SUB-PROGRAMME | ACTIVITY/PROJECT/OPERATION | LOCATION | SDG TARGETS | BASELINE | OUTPUT INDICATOR | QUARTERLY TIME SCHEDULE |  |  |  | SOURCE OF FUNDING |  |  |  |  | IMPLEMENTING AGENCIES
[7 empty] | 1ST | 2ND | 3RD | 4TH | DACF | RFG/DDF | IGF | DP | MPs Fund | LEAD | COLLABORATOR
Social Service Delivery | Education & Youth Development | Construction of 1No.2-storey 6-unit classroom block ancillary facilities at Somanya Methodist | Somanya | 4.a |  | 1No.2-storey 6-unit classroom block with ancillaries constructed | X | X | X | X |  | 29892.58
|  | Construction of 1No.3-unit classroom block,office and store with 1No.3-seater KVIP toilet | Obawale | 4.a |  | 1No.3-unit classroom block,office and store with 1No.3-seater KVIP toilet constructed | X | X | X | X |  | 143924.5
|  | Supply of furniture(200No dual desk,8No.teachers' table & 6No teachers' chair) for Somanya Methodist school | Somanya | 4.a |  | 200No.dual desk,8No.teachers' table and 6No.teachers'chair supplied | X | X | X | X |  | 42506.21
|  | Construction of 1No.2-unit classroom block with office,store and 2-seater KVIP toilet | Sokwenya | 4.a |  | 1No.2-unit classroom block with office,store and 2-seater KVIP toilet constructed | X | X | X | X |  |  |  |  | 110138.57
|  | Cladding of 1No.6-unit primary classroom block. | Sikalehia | 4.a |  | 1No.6-unit primary classroom cladded | X | X | X | X | 60695.99
|  | Construction of 1No.3-unit classroom block,office and store with 1No.3-seater KVIP toilet | Brukum Agavenya | 4.a |  | 1No.3-unit classroom block,office and store with 1No.3-seater KVIP toilet constructed | X | X | X | X | 201932.11
|  | Support brilliant but needy students and STME programme | [8 empty] | 45000
|  | Construction of perimetre fence wall at Somanya Presby | Somanya | 4.a |  | Perimetere fence wall constructed | X | X | X | X | 10459.94
|  | Construction of 1No.3-unit classroom block,office and store with 1No.3-seater KVIP toilet | Tsremati-Yoyim | 4.a |  | 1No.3-unit classroom block,office and store with 1No.3-seater KVIP toilet constructed | X | X | X | X | 302903.17
| Health Delivery | Renovate the Ghana Health Directorate office and pave the frontage. | Somanya | 3.8 |  | Ghana health directorate office renovated and frontage paved | X | X | X | X | #
|  | Provision of furniture,medical equipment and instrument for Samlese and Aplese CHPs zones | Samlese and Aplese zones | 3.8 |  | Furniture,medical equipment and instruments provided | X | X | X | X | #
|  | Expansion & renovation of Samlese and Aplese CHPS Zones | Samlese and Aplese zones | 3.8 |  | Samlese and Apele CHPs compounds expanded and renovated | X | X | X | X | #
|  | Provide medical instrument and equipment for Akorwu Bana CHPS Zones | Akorwu Bana | 3.8 |  | Medical instrument and equipment for Akorwu Bana CHPs compund provided | X | X | X | X | #
|  | Complete construction of Ahinkwa CHPs compound | Ahinkwa | 3.8 |  | CHPS compound completed | X | X | X | X | 66603.97
|  | Rehabilitate and expand Akpamu CHPS Zone | Akpamu | 3.8 |  | CHPs compound expanded and rehabilitated | X | X | X | X | #
|  | Provision of borehole,equipment,instrument and furniture for Ahinkwa and Aketebuor CHPs compound | Ahinkwa and Aketebuor | 3.8 |  | Borehole,medical equipment,instrument and furniture provided | X | X | X | X | #
|  | Construction of 1No.CHPs compound | Huhunya | 3.8 |  | 1No.CHPs compound constructed | X | X | X | X |  |  |  |  | 109968.08
|  | Complete construction of CHPs compound | Akorley. | 3.8 |  | CHPs compound completed | X | X | X | X | 44969.2
|  | Construction of CHPS compound and borehole | Aketebuor | 3.8 |  | CHPs compound completed | X | X | X | X |  | 129314.13
ADOPTED GOAL:Saveguard The Natural Environment & Ensure A Resilient, Built Environment
Environmental & Sanitation management | Disaster Prevention & Management | Educate the public on the need to acquire permanent and temporal permits | Municipality-wide |  |  | Number of Education carried out | X | X | X | X |  |  | #
Procurement of 100No.streetlights
Procurement of accessories for maintenance of streetlights
|  | Educate and sensitize the public on bush fires and flood across the 7 Zones | Municipality-wide |  |  | Number of sensitisation programme undertaken | X | X | X | X |  |  | #
|  | Formation of disaster volunteer groups (11 groups) | Municipality-wide |  |  | Number of groups formed | X | X | X | X |  |  | #
|  | Construction of 10-seater W/C toilet with mechanised borehole | Ogome |  |  | 10-seater W/C toilet with borehole constructed | X | X | X | X | 14956.31
|  | Construction of 10-seater W/C toilet with mechanised borehole | Abokobi |  |  | 10-seater W/C toilet with borehole constructed | X | X | X | X | 16829.2
|  | Acquire 2No. Final Disposal Sites for 2No. communities (Somanya and Nkurakan) | Somanya and Nkurakan |  |  | 2No.final disposal sites acquired | X | X | X | X |  |  | #
|  | Evacuate refuse from dumping site to final disposal sites | Municipality-wide |  |  | Refuse evacuated | X | X | X | X |  |  | #
Management of final waste disposal site
Sanitation improvement package
|  | Disinfestation, disinfection and maintenance of solid and liquid waste disposal sites | Municipality-wide |  |  | Disinfestation,disinfection and maintenece of solid and liquid waste disposal sites carried out | X | X | X | X |  |  | #
|  | Construction of storm drains at Somanya lorry park | Somanya |  |  | Storm drains constructed | X | X | X | X |  | 19956.5
|  | Construction of access roads to new sites at Somanya, Nkurakan, Agogo, Aboabo | Municipality-wide |  |  | Number of access road constructed | X | X | X | X |  |  | #
|  | Intensify the supervision of Zoomlion activities within the municipality | Municipality-wide |  |  | Number of activities supervised | X | X | X | X |  |  | #
|  | Training of staff and community members on the prevention of drowning. | Somanya |  |  | Number of people trained | X | X | X | X |  |  | #
|  | Construction of 3No.boreholes | Plechie,Abrewankor & Brukum-maumi |  |  | 3no.boreholes constructed | X | X | X | X |  |  |  |  | 1414.14
Infrastructure Delivery & Management | Infrastructure Development | Reshaping of 8km feeder roads | Selected feeder roads |  |  | 8km feeder roads reshaped | X | X | X | X | #
|  | Provide Overhead Polytank for Agric directorate | Somanya |  |  | Overhead polytank provided | X | X | X | X | #
Purchase and documentation of land for development projects
|  | Construction of access road to fortifier fertiliser factory(55m) | Akorley,Somanya |  |  | 55m access road constructed | X | X | X | X | 89171.5
ADOPTED GOAL:Maintain A stable,United & Safe Society
Management & Administration | Human Resource development & Management | Revise and implement the Municipal Gender Profile | Somanya |  |  | Gender profile revised | X | X | X | X | #
Capacity building for staff and Assembly members
|  | Procurement of 11No swivel chair,1No.office desk,2No.desktops,1No scanner,2No.printer & 2No.laptops | [13 empty] | Cadmin
|  | Organise 2No.technical training for 40No.clients | [8 empty] | 9200 |  |  |  |  | BAC
|  | Organise 4No.management training for 50No. Clients | [8 empty] | 9800 |  |  |  |  | BAC
|  | Prepare the Gender Action Plan for 2021 | Somanya |  |  | Gender action plan prepared | X | X | X | X | #
|  | Facilitate adult education/functional literacy on topical issues and alternative livelihood empowerment programmes | Somanya |  |  | Functional literacy/adult education on livelihood programmes carried out | X | X | X | X | #
|  | Conduct education in communities on child protection issues | Somanya |  |  | Number of education on child protection carried out | X | X | X | X | #
|  | Facilitate PWD led engagement meetings per zone on Local governance Act 2016 Act 936 | Somanya |  |  | Number of meetings carried out | X | X | X | X | #
|  | Provide probation services to the court and family tribunal sittings | Somanya |  |  | Services provided | X | X | X | X |  |  | #
|  | Train women groups in skills acquisition | Somanya |  |  | Number of women groups trained | X | X | X | X | #
|  | Renovate the Magistrate, Human Resource ,MPO,MBO official bungalows | Somanya |  |  | Number of bungalows renovated | X | X | X | X | 68614.95
|  | Renovate Assembly office building | Somanya |  |  | Assembly building renovated | X | X | X | X | #
|  | Renovation of office accommodation,construction of 2No.cells and 3-seater W/C for District magistrate court | Somanya |  |  | Office accommodation,2No.cells and 3-seater W/C renovated and constructed respectively | X | X | X | X | 68614.95
|  | Renovate Works Dept. Office | Somanya |  |  | Works Department renovated | X | X | X | X | #
|  | Renovation of deputy director's bungalow | Somanya |  |  | Bungalow renovated | X | X | X | X | 66051.04
|  | Construction of a police post | Klo-Agogo |  |  | Police post constructed | X | X | X | X | 128856.61
| Finance & Revenue Mobilisation | Educate and sensitize the public on the payment of property rate | Municipality-wide | 17.1 |  | Number of sensitisation programme undertaken | X | X | X | X |  |  | #
|  | Implemntation of Revenue Improvement Action Plan(RIAP) | [8 empty] | 30000 |  | 20000
|  | Train revenue staff and Zonal Councils Members on revenue collection | Somanya | 17.1 |  | Number of revenue staff trained | X | X | X | X |  |  | #
|  | Installation of software for revenue collection | Somanya | 17.1 |  | Software installed | X | X | X | X | #
| Planning,Budgeting & Co-ordination | Monitoring and evaluation of development projects and programmes | [8 empty] | 60000
Organise 4No.mandatory 5Nosubcommittee,executive committee and General assembly
|  | Organisation of stakeholder consultative/town hall meetings and public education | [8 empty] | 90000
|  | Valuation of immovable properties | [8 empty] | 40000
ADOPTED GOAL:Build A Prosperous Society
Economic Development | Trade,Tourism & Industrial Development | Train farmers on the introduction of hybrid seed-maize | Somanya |  |  | Number of farmers yrained | X | X | X | X | #
|  | Sensitize/Educate the public on the formation of Co-operative Societies | Municipality-wide |  |  | Number of sensitisation programme undertaken | X | X | X | X | #
|  | Register and audit/inspect Co-operative Societies. | Municipality-wide |  |  | Number of co-operatives inspected/audited | X | X | X | X | #
|  | Organize women groups to create awareness on entrepreneurship development | Municipality-wide |  |  | Number of women groups organised | X | X | X | X | #
|  | Construct 1No. slaughter house | Somanya |  |  | Slaughterhouse constructed | X | X | X | X |  | 374000
|  | Assist co-operative members to access low terms of interest loans | Municipality-wide |  |  | Number of co-operative members assisted | X | X | X | X | #
|  | Introduce women into various types of Cooperative groups | Municipality-wide |  |  |  | X | X | X | X | #
|  | Construction of Kenkey shed | Somanya |  |  |  | X | X | X | X |  |  |  |  | 8061.97
|  | Construction of 1No.10-unit market shed | Oterkpolu |  |  |  | X | X | X | X |  |  |  |  | 15341.65
|  | Rehabilitation of market centre(Phase I) | Klo-Agogo |  |  |  | X | X | X | X |  | 19969.7
|  | Paving of Somanya lorry park(Phase 1) | Somanya